## Sheet1
plotID | plotType | priority | speciesCount | 23order | 24order | 25order | sampled | date | initials | notes | DIV Progress Tracker
DELA_001 | distributed | 4 | 103 | 2.6 | 11 | 5.1 |  |  |  |  | Completed plots | 0 | Scheduled days left | 16
DELA_002 | distributed | 6 | 80 | 3.1 | 3 | 4.2 |  |  |  |  | Remaining top 20 | 20 | Plots per day | 2
DELA_003 | distributed | 7 | 117 | 3.2 | 5 | 6.1 |  |  |  |  | Remaining total | 33 | Estimated plots complete | 32
DELA_004 | distributed | 8 | 113 | 2.2 | 4 | 4.1
DELA_005 | distributed | 10 | 114 | 4.2 | 15 | 7.2 |  |  |  |  | DIV Dates (2025)
DELA_006 | distributed | 11 | 119 | 5.1 | 17 | 8.1 |  |  |  |  | Start | 2025-07-21
DELA_008 | distributed | 15 | 60 | 7.1 | 10 | 10.2 |  |  |  |  | End | 2025-08-20
DELA_009 | distributed | 17 | 74 | 4.3 | 6 | 6.2 |  |  |  |  | Sampling days | 16
DELA_011 | distributed | 12 | 69 | 4.1 | 8 | 7.1
DELA_012 | distributed | 21 | 94 | 2.4 |  | 3.2
DELA_013 | distributed | 14 | 87 | 6.3 | 18 | 9.1
DELA_014 | distributed | 5 | 89 | 2.3 | 2 | 3.1
DELA_015 | distributed | 18 | 80 | 7.2 | 14 | 12.1
DELA_016 | distributed | 9 | 142 | 8.1 | 20 | 11
DELA_017 | distributed | 22 | 98 | 8.2 |  | 5.2
DELA_018 | distributed | 23 | 103 | 8.4 |  | 14.2
DELA_020 | distributed | 25 | 83 | 8.5 |  | 14.1
DELA_021 | distributed | 19 | 76 | 7.3 | 19 | 12.2
DELA_022 | distributed | 26 | 70 | 10.1 |  | 9.2
DELA_023 | distributed | 27 | 76 | 10.2 |  | 10.1
DELA_025 | distributed | 13 | 114 | 6.1 | 12 | 8.2
DELA_026 | distributed | 16 | 114 | 6.2 | 13 | 8.3
DELA_027 | distributed | 20 | 91 | 7.4 | 16 | 13.1
DELA_028 | distributed | 24 | 89 | 8.3 |  | 13.2
DELA_029 | distributed | 28 | 84 | 9.1 |  | 15.2
DELA_030 | distributed | 31 | 102 | 11.1 |  | 16.1
DELA_037 | tower | 1 | 124 | 1.1 | 7 | 1.1
DELA_038 | tower | 2 | 96 | 1.2 | 9 | 2.1
DELA_040 | tower | 3 | 89 | 1.3 | 1 | 2.2
DELA_060 | distributed | 29 | 72 | 9.2 |  | 15.1
DELA_061 | distributed | 30 | 49 | 2.5 |  | 16.2
DELA_062 | distributed | 32 | 63 | 11.2 |  | 17.2
DELA_063 | distributed | 33 | 70 | 10.3 |  | 17.1