## Sheet2
plotID | plotType | swamp | priority | speciesCount | 23order | 24order | 25order | sampled | date | initials | notes | DIV Progress Tracker
LENO_003 | distributed | lower | 5 | 93 | 4 | 4 | 1 |  | 2025-06-16 |  |  | Completed plots | 0 | Scheduled days left | 16
LENO_062 | tower | upper | 3 | 106 | 1 | 1 | 2 |  | 2025-06-17 |  |  | Remaining top 20 | 20 | Plots per day | 1.5
LENO_001 | distributed | upper | 7 | 117 | 13 | 30 | 3 |  | 2025-06-17 |  | MUD PLOT | Remaining total | 33 | Estimated plots complete | 24
LENO_010 | distributed | lower | 12 | 90 | 6 | 5 | 4 |  | 2025-06-18
LENO_004 | distributed | lower | 6 | 114 | 8 | 9 | 5 |  | 2025-06-18
LENO_063 | tower | upper | 2 | 104 | 2 | 2 | 6 |  | 2025-06-19
LENO_061 | tower | upper | 1 | 137 | 12 | 3 | 7 |  | 2025-06-23
LENO_012 | distributed | lower | 14 | 114 | 11 | 13 | 8 |  | 2025-06-24
LENO_009 | distributed | lower | 11 | 88 | 10 | 12 | 9 |  | 2025-06-24
LENO_008 | distributed | lower | 17 | 105 | 7 | 7 | 10 |  | 2025-06-25 |  | Timber rattlers in this plot - be careful
LENO_006 | distributed | lower | 9 | 89 | 5 | 6 | 11 |  | 2025-06-25
LENO_007 | distributed | lower | 10 | 99 | 15 | 20 | 12 |  | 2025-06-26
LENO_021 | distributed | upper | 15 | 120 | 20 | 31 | 13 |  | 2025-06-30
LENO_005 | distributed | lower | 8 | 115 | 9 | 10 | 14 |  | 2025-07-01
LENO_011 | distributed | lower | 13 | 131 | 17 | 11 | 15 |  | 2025-07-01 |  | Stream going through plot
LENO_013 | distributed | lower | 16 | 97 | 18 | 17 | 16 |  | 2025-07-02
LENO_014 | distributed | lower | 18 | 119 | 24 | 23 | 17 |  | 2025-07-02
LENO_015 | distributed | lower | 19 | 82 | 22 | 8 | 18 |  | 2025-07-03
LENO_022 | distributed | lower | 20 | 89 | 16 | 15 | 19 |  | 2025-07-07 |  | MUD PLOT
LENO_002 | distributed | lower | 4 | 146 | 3 | 26 | 20 |  | 2025-07-08
LENO_027 | distributed | lower | 22 | 93 | 26 | 16 | 21 |  | 2025-07-08
LENO_016 | distributed | lower | 21 | 120 | 23 | 27 | 22 |  | 2025-07-09 |  | MUD PLOT
LENO_019 | distributed | lower | 24 | 125 | 19 | 19 | 23 |  | 2025-07-09
LENO_017 | distributed | upper | 23 | 138 | 21 | 32 | 24 |  | 2025-07-10
LENO_023 | distributed | lower | 25 | 116 | 28 | 14 | 25
LENO_018 | distributed | lower | 26 | 91 | 14 | 25 | 26
LENO_024 | distributed | lower | 27 | 82 | 25 | 28 | 27
LENO_020 | distributed | lower | 28 | 98 | 27 | 21 | 28
LENO_025 | distributed | lower | 29 | 29 | 31 | 22 | 29 |  |  |  | WATER PLOT
LENO_029 | distributed | upper | 30 | 118 | 32 | 33 | 30
LENO_026 | distributed | lower | 31 | 58 | 29 | 29 | 31 |  |  |  | WATER PLOT
LENO_030 | distributed | lower | 32 | 104 | 30 | 24 | 32 |  |  |  | MUD PLOT
LENO_028 | distributed | lower | 33 | 107 | 33 | 18 | 33