## tracker
plotID | plotType | nlcdClass | elevationM | priority | speciesCount | 22order | 23order | 24order | 25order | sampled | date | initials | genArc | notes | DIV Progress Tracker
TALL_044 | tower | evergreenForest | 129.14 | 1 | 166 | 21 | 3 | 23 | 9.2 |  |  |  |  | Surprising open for how many species there are here, west side is slightly more open and is thicker | Completed plots | 0 | Scheduled days left | 16
TALL_051 | tower | mixedForest | 116.77 | 2 | 147 | 22 | 2 | 14 | 5.1 |  |  |  |  | Took two half days to finish half a plot with 3 people; south sides takes longer and is more dense | Remaining top 20 | 20 | Plots per day | 1.5
TALL_054 | tower | evergreenForest | 123.25 | 3 | 100 | 23 | 1 | 15 | 9.1 |  |  |  |  | Took 1 day to finish the plot with three people; make sure to line up in theright spot, the hills make the orientation here confusing | Remaining total | 33 | Estimated plots complete | 24
TALL_004 | distributed | evergreenForest | 132.22 | 4 | 117 | 18 | 4 | 19 | 8.1 |  |  |  |  | full sun DO IN THE MORNING
TALL_001 | distributed | deciduousForest | 100.25 | 5 | 64 | 1 | 5 | 4 | 2.1 |  |  |  |  | Team one starts here, moves to 002 when finished, DO HERB CLIP | DIV Dates (2025)
TALL_002 | distributed | mixedForest | 114.88 | 6 | 124 | 13 | 7 | 11 | 3.2 |  |  |  |  | Have the beetle team check when Prunus is blooming + collect | Start | 2025-08-25
TALL_006 | distributed | evergreenForest | 99.04 | 7 | 157 | 16 | 8 | 21 | 7.2 |  |  |  |  | HERB CLIP | End | 2025-09-26
TALL_007 | distributed | deciduousForest | 83.92 | 8 | 99 | 2 | 6 | 3 | 2.2 |  |  |  |  | Team two starts here, moves to 002 to help when finished, DO HERB CLIP | Sampling days | 16
TALL_003 | distributed | mixedForest | 120.8 | 9 | 159 | 19 | 10 | 22 | 6.1 |  |  |  |  | full sun; leave early; HERB CLIP
TALL_009 | distributed | evergreenForest | 108.91 | 10 | 177 | 20 | 11 | 24 | 10.1 |  |  |  |  | full sun
TALL_008 | distributed | deciduousForest | 113.4 | 11 | 103 | 4 | 13 | 1 | 1.1
TALL_005 | distributed | mixedForest | 121.47 | 12 | 155 | 7 | 12 | 8 | 6.2 |  |  |  |  | full sun
TALL_013 | distributed | evergreenForest | 118.63 | 13 | 103 | 14 | 9 | 20 | 7.1 |  |  |  |  | Took all day, very diverse plot, cool orchids, easy to get to
TALL_010 | distributed | deciduousForest | 124.1 | 14 | 123 | 5 | 14 | 7 | 3.1
TALL_012 | distributed | mixedForest | 136.19 | 15 | 83 | 8 | 15 | 5 | 5.2
TALL_016 | distributed | evergreenForest | 103.6 | 16 | 105 | 17 | 19 | 17 | 8.2
TALL_011 | distributed | deciduousForest | 83.37 | 17 | 127 | 6 | 18 | 10 | 4.1 |  |  |  |  | Walk along Mayfield to get to, take AP or KP
TALL_017 | distributed | mixedForest | 120.93 | 18 | 97 | 9 | 16 | 6 | 11.1
TALL_018 | distributed | evergreenForest | 126.48 | 19 | 62 | 15 | 17 | 16 | 11.2
TALL_015 | distributed | deciduousForest | 108.6 | 20 | 65 | 3 | 20 | 2 | 12.1
TALL_025 | distributed | mixedForest | 114.54 | 21 | 102 | 11 | 21 | 12 | 12.2 |  |  |  |  | all cane - do when you're leaving
TALL_020 | distributed | evergreenForest | 126.15 | 22 | 101 |  |  | 18
TALL_022 | distributed | deciduousForest | 120.23 | 23 | 105 | 10 |  | 9
TALL_029 | distributed | mixedForest | 120.26 | 24 | 117 |  |  | 25 | [5 empty] | full sun
TALL_021 | distributed | evergreenForest | 117.65 | 25 | 78 | 25 |  | 31 | [5 empty] | do same day as 30
TALL_023 | distributed | deciduousForest | 110.92 | 26 | 120 |  |  | 26 | [5 empty] | will take a long time to get to
TALL_030 | distributed | mixedForest | 92.55 | 27 | 74 | 24 |  | 32 | [5 empty] | do same day as 21
TALL_026 | distributed | evergreenForest | 102.98 | 28 | 115 |  |  | 27
TALL_024 | distributed | deciduousForest | 128.32 | 29 | 129 |  |  | 28
TALL_032 | distributed | mixedForest | 120.41 | 30 | 113 |  |  | 29
TALL_031 | distributed | evergreenForest | 133.99 | 31 | 111 | 12
TALL_027 | distributed | deciduousForest | 93.04 | 32 | 97
TALL_064 | distributed | mixedForest | 96.31 | 33 | 130